## Timeline
POS System: 10-week project timeline
Project start (Monday of week 1) | 2026-07-06 | Plan start date. Change it and every week updates.
Week | Starts | Ends | Phase | Tasks | Marks component | Status | Evidence (commits and files)
1 | 2026-07-06 | 2026-07-12 | Setup and documents | Create the team repo and report folders. Upload the backend. Write the idea, abstract and feature list. Set up the frontend config and Redux Toolkit part 1. Write the Postman testing report and the commit log. | Idea & Abstract, Weekly Progress, Implementation, Testing | Done | e154036, 2016d55, 76f7ec5, ae83e2e, b4a6f5a, 6891d41 to 5e1ae71 (12 Redux commits), ba6b43c, ba99aad, c61014c
2 | 2026-07-13 | 2026-07-19 | Design and SRS | Commit the UML and ER diagrams. Write the SRS in IEEE format. Finish Redux part 2 and globleState.js. Push the Branch Manager and Cashier pages. | SRS, Design, Implementation | In progress | Diagrams made, commit pending. Customers.jsx added by a teammate. Redux part 2 assigned to Subhash.
3 | 2026-07-20 | 2026-07-26 | Frontend: auth and super admin | Login, forgot password, reset password, onboarding and landing page. Super admin dashboard, stores, pending requests and subscription plans. | Implementation | Planned
4 | 2026-07-27 | 2026-08-02 | Frontend: store admin | Branches, categories, products, employees, inventory, store dashboard and alerts. | Implementation | Planned
5 | 2026-08-03 | 2026-08-09 | Frontend: branch manager and cashier | Branch manager orders, refunds, inventory, reports. Cashier POS screen, returns, order history, customer lookup and shift summary. | Implementation | Planned
6 | 2026-08-10 | 2026-08-16 | Payments and subscriptions | Razorpay and Stripe checkout, subscription upgrade, payment status and email receipts. | Implementation | Planned
7 | 2026-08-17 | 2026-08-23 | Testing | Run the Postman collection with all role tokens and record results. Add negative and security tests. Write unit tests for key services. | Testing | Planned | Report and 96 test cases written, results to be recorded.
8 | 2026-08-24 | 2026-08-30 | Code quality and fixes | Axios interceptor, logout fix, API URL in env file, remove console logs, fix security findings, update README. | Implementation & Code Quality | Planned
9 | 2026-08-31 | 2026-09-06 | Presentation and viva prep | Report PPT, demo script, viva questions and final documents. | Presentation, Demo & Viva | Planned
10 | 2026-09-07 | 2026-09-13 | Final demo and submission | Full demo run, final checks, final commit log and submission. | Demo & Viva, Weekly Progress | Planned
Weeks 2 to 10 are a suggested plan. Replace them with your official timeline if you have one, and set Status as the work moves.
Done weeks | 1
In progress | 1
Planned | 8
Formulas:
Starts = B3+7*([Week]-1)
Ends = [Starts]+6

## Done so far
Work completed so far
# | Item | Marks component | Week | Evidence | Status
1 | Team repo created and report folders set up | Weekly Progress | 1 | ae83e2e, 0de054b | Done
2 | Full Spring Boot backend uploaded | Implementation | 1 | 76f7ec5 | Done
3 | Project idea, abstract and objectives | Idea & Abstract | 1 | e154036 | Done
4 | Features, modules and tech stack | SRS / Documentation | 1 | 2016d55 | Done
5 | Frontend config, API client and utils | Implementation | 1 | b4a6f5a | Done
6 | Redux Toolkit part 1: adminDashboard, auth, branch, branchAnalytics, cart, category, customer, employee, inventory, onboarding, order | Implementation | 1 | 6891d41, fa37aff, b800862, 59c7e45, 3742915, 391ed0a, c59138e, ded8c80, 7fd0937, ce4e04a, 5e1ae71 | Done
7 | Commit log updated | Weekly Progress | 1 | ba6b43c | Done
8 | Postman testing report (2 parts) | Testing | 1 | ba99aad, c61014c | Done
9 | API test case sheet (96 cases) | Testing | 1 | POS_Backend_Test_Cases.xlsx | Made, not committed
10 | UML, ER and architecture diagrams (20) | Design | 1 | POS_UML_Diagrams_v2 | Made, not committed
11 | README updated | Implementation | 1 | README.md | Made, not committed
12 | Branch Manager Customers page | Implementation | 1 | Teammate commit, see git log | Done by teammate
13 | Cashier pages | Implementation | 2 | Teammate, not pushed yet | In progress
14 | Redux Toolkit part 2 and globleState.js | Implementation | 2 | Subhash, not pushed yet | In progress
| Done | 9
| Made, not committed | 3
| In progress | 2

## Marks tracker
Progress by marks component
Component | Marks | Status | Notes
Idea & Abstract | 5 | Done | Committed in reports.
SRS / Documentation | 10 | Not started | IEEE format SRS still to be written.
Design (Use-case, Class, ER) | 10 | Started | Diagrams made, commit pending.
Weekly Progress (tracking sheet) | 25 | Started | Commit log and this timeline. Update every week.
Implementation & Code Quality | 20 | Started | Backend and Redux part 1 done, pages in progress.
Testing | 10 | Started | Report and test cases written, results to be recorded.
Presentation | 10 | Not started
Demo & Viva (individual) | 10 | Not started
Total marks | 100
Marks with work started or done | 70
Share of marks started | 70%